## Лист1
COVID-19 Self-Assessment Test
First Sprint
S.no | Task Priority | Task | Person Name | Hours | Sprint Status | Time
1 | Top | Over view Project Requirements | both |  | Done | 15
2 | Top | Paper Prototype | Ali |  | Done | 9
3 | Medium | Setup Environment | Abhi |  | Done | 7 | finished
4 | Top | Solution Generations for UI | Ali |  | Done | 12
5 | Medium | Home Page Complete creations | Abhi |  | Done | 18
6 | Medium | Testing | Ali |  | Done | 3
7 | Top | Webpages Service and Your Health | Ali |  | Done | 4
[5 empty] | Total Hrs this Sprint | 68
Second Sprint
S.no | Task Priority | Task | Person Name | Hours | Sprint Status | Time
1 | Medium | Text decoration (webpages) | Abhi |  | Done | 5
2 | Top | Setup environment with Python (flask web ) | Ali |  | Done | 7
3 | Medium | Incremental Testing/ find best solution for the system | Abhi |  | Done | 4
4 | low | FAQ Page and subscription button with data base | Abhi |  | Done | 6 |  | finished
5 | Top | Page linking with Flask ( Service, health, result ) | Abhi |  | Done | 4
6 | Medium | Create and deploy Self Assignment form and result page | Both |  | Done | 5
7 | Medium | Write Content of coronavirus | Ali |  | Done | 3
8 | Medium | black box Testing | Ali |  | Done | 2
9 | low | Web pages contact us, live chat support | Abhi |  | Done | 5
10 | Top | Create a "Scroll to Top" | Ali |  | Done | 2
11 | Top | Corona Data Fectch form API | Ali |  | Done | 15
12 | low | Text decoration (webpages) | Ali |  | Done | 6
13 | Top | Page linking with Flask (Index, home, Stauts) | Ali |  | Done | 1
14 | Medium | clone project and testing | both own systems |  | Done | 7
15 | Medium | Demo Phase 1 | both |  | Done | 1
16 | Top | Self Assessement Trainning model (panda, numpy , logistics regression) | Abhi |  | Done | 3
[5 empty] | Total Hrs this Sprint | 76
Third Sprint
S.no | Task Priority | Task | Person Name | Hours | Sprint Status | Time
1 | Medium | Contact page create and link with falsk | Abhi |  | Done | 3 |  |  |  | finished
2 | Top | Corona Database Fetch form Api | Ali |  | Done | 16
3 | Medium | Current Status UI and Link with flask | Ali |  | Done | 3
4 | low | live chat integration with contact page and falsk | Abhi |  | Done | 9
5 | Medium | Database intergrate with Flask gun and Contact page together | Both |  | Done | 7
6 | Top | Contact form with Database | Abhi |  | Done | 4
7 | low | Write Content of Status and Add Features | Both |  | Done | 5
8 | Top | Test moudle and all pages | Both |  | Done | 5
9 | Medium | Integration Testing Phase 1 (User input in self Ass test) | Abhi |  | Done | 3
10 | Medium | Integration Testing Phase 2 (User input coutnry name and status) | Ali |  | Done | 3
11 | low | Add some features in Yourhealth Page | Abhi |  | Done | 7
12 | Medium | test the interface after intergration all Web pages with flask | both |  | Done | 3
13 | Medium | Create tables with filter (cities contact number ) | both |  | Done | 4
[5 empty] | Total Hrs this Sprint | 72
Forth Sprint
1 | Top | Sqlite3 Database | Abhi |  | Done | 12
2 | Top | intergration UI Contact Form With Database | Abhi |  | Done | 5
3 | Top | intergration UI Subcription With Database | Ali |  | Done | 7 |  |  | finished
4 | Top | Documentation | both |  | Done | 15
5 | Top | Presentation | both |  | Done | 4
[5 empty] | Total Hrs this Sprint | 43